## Sheet2
Weeks | Delivery |  | Activity | Task | Task Dependency
09/02-09/08 | Positioning Coordinate Generation | Administration, Research | Find Version Control | List of Possible SCM
|  |  |  | Initial Commit | List of Possible SCM
|  |  | Find Coordinate Generation method/service | List of Possible Pos. Systems w/ Pro et Contra
09/09-09/15 |  | Implementation | Design
Test Cases
|  |  | Implement | Mutually exclusive coding sections
Testing
Refactoring
Delivery 1
09/16-09/22 | Design Spec | Research, Architecture | Create Test Scenarios
Update Iteration Plan
|  |  | Research Storage/Authentication methods | List of Possible Storage/DB solutions with Pro et Contra
List of Possible Authentication methods with Pro et Contra
Generate Architecture Document
09/23-09/29 |  | Create Design & Review | Create Detailed Design Doc. | Produce Positioning System Design
Positioning Storage Design
Secure Authentication Design
CoS Integration Design
Review Complete Design Doc.
Delivery 2
09/30-10/06 | Positioning Coordinate Storage System | Implementation | Scenarios
Update Iteration Plan
API/Interface
Generate Test Cases
|  |  | Implementation | Mutually exclusive coding sections
10/07-10/13 |  | Review & Refactoring | Testing
Update Design Doc
|  |  | Refactoring | Mutually exclusive coding sections
Delivery 3
10/14-10/20 | Secure Authentication System | Implementation | Update Iteration Plan, update design
Generate Test Cases
|  |  | Implementation | Mutually exclusive coding sections
10/21-10/27 |  | Review & Refactoring | Testing
Update Design Doc
|  |  | Refactoring | Mutually exclusive coding sections
Delivery 4
10/28-11/03 | User Interface | UI Design | Update Iteration Plan
Use Scenarios
Update Iteration Plan
UI Prototypes
|  |  | Code Interface | Mutually exclusive implementation sections(if possible)
11/04-11/10 |  | Implementation | Test UI
|  |  | Readjustments | Mutually exclusive implementation sections(if possible)
Delivery 5
11/11-11/17 | Cone of Silence Integration | Implementation | Update Iteration Plan
Update Design Doc
Generate Test Cases
|  |  | Implementation | Mutually exclusive coding sections
Add Code to CoS system
11/18-11/24 |  | Testing & Packaging | Test Integrated CoS system
Package code within CoS system
Apply Test Scenarios
Delivery 6